## 00_Dashboard
NARENDRA KUMAR — INTERVIEW COMMAND CENTER
Interview: 16 Aug 2026 ¦ Effort window: 13–15 Aug ¦ Goal: Perform better with depth (not perfection)
OVERALL PROGRESS |  | DSA PROBLEMS |  | RESUME / HR |  | CS CORE
| / 33 tasks |  | / 12 |  | / 11 |  | / 14
TODAY FOCUS (read this first)
Date | Priority Focus | Hours | Must Finish Before Sleep
Thu 13 Aug (Tonight) | 4 DSA + Intro B + Nyay + PK/FK + Process/Thread | 2.5–3 hrs | Two Sum, Duplicate, Stock, Parentheses + Intro spoken
Fri 14 Aug (Main Day) | Window/LL/BS/Tree + CS flash + full resume speak | 4–5 hrs | Reverse LL, Binary Search, Tree depth + HR answers
Sat 15 Aug (Polish) | Fails only + Full mock + sleep early | 3–4 hrs | Full mock done + no new topics
Sun 16 Aug (Interview) | Intro + Nyay only (15 min). Stay calm. | light | Clarify→Example→Brute→Better→Code→Complexity
HOW TO USE (simple)
1. Work mainly in sheet 01_Master_Plan — mark Status = Done only if you can explain out loud.
2. For every DSA problem: write Brute idea + Optimal idea, then code Optimal.
3. Orange Priority = MUST. Do MUST before SHOULD.
4. Use 03_Resume_HR for speaking practice. Record yourself once.
5. Do not add random YouTube topics. This sheet is enough for a fresher technical round baseline.
6. Target before interview morning: Overall >= 75% Done.
FILE PATHS
Local folder: E:\sems\sem 7\Python DSA
Intro PDF: Resume_Prep\Narendra_Interview_Intro.pdf
HR PDF: Resume_Prep\Narendra_Interview_Behavioural.pdf
GitHub: https://github.com/knarendrakumar187/Python-DSA-Interview-Prep
MINDSET
You are not behind forever. You are 3 focused days away from a clearer interview. Depth > panic. Start Task #1 now.

## 01_Master_Plan
01 — MASTER PLAN (13 Aug night → 16 Aug)
Mark Status with dropdown. MUST rows are critical. Progress auto-counts on Dashboard.
Filter by Date/Priority using the dropdown arrows in the header row.
# | Date | Block | Task | Category | Priority | Mins | Status | Resource / File | My Notes
1 | Thu 13 Aug | Night-1 | Solve Two Sum (explain brute + code hash map) | DSA | MUST | 25 | Not Started | Day01_02_Arrays/Day01_problems.py
2 | Thu 13 Aug | Night-1 | Solve Contains Duplicate | DSA | MUST | 15 | Not Started | Day01_problems.py
3 | Thu 13 Aug | Night-1 | Solve Best Time to Buy and Sell Stock | DSA | MUST | 20 | Not Started | Day01_problems.py
4 | Thu 13 Aug | Night-1 | Solve Valid Parentheses (stack) | DSA | MUST | 20 | Not Started | Day07_Stack_Queue/Day07_problems.py
5 | Thu 13 Aug | Night-2 | Speak Intro Version B three times with timer | Resume | MUST | 15 | Not Started | Resume_Prep/INTRO.md or PDF
6 | Thu 13 Aug | Night-2 | Speak Nyay Sahayak: What + RAG + 1 difficulty | Resume | MUST | 20 | Not Started | Resume_Prep/PROJECT_DEPTH.md
7 | Thu 13 Aug | Night-2 | CS speak: Primary key vs Foreign key + JOIN types | CS | MUST | 20 | Not Started | CS_Core/DBMS_SQL
8 | Thu 13 Aug | Night-2 | CS speak: Process vs Thread with example | CS | MUST | 10 | Not Started | CS_Core/OS
9 | Fri 14 Aug | Morning | Solve Move Zeroes (in-place two pointer idea) | DSA | MUST | 20 | Not Started | Day01 / arrays
10 | Fri 14 Aug | Morning | Solve Valid Palindrome (two pointers) | DSA | MUST | 20 | Not Started | Day04_Two_Pointers
11 | Fri 14 Aug | Morning | Attempt Longest Substring Without Repeating | DSA | MUST | 35 | Not Started | Day05_Sliding_Window
12 | Fri 14 Aug | Morning | Reverse Linked List + draw prev/curr/next | DSA | MUST | 30 | Not Started | Day08_LinkedList
13 | Fri 14 Aug | Morning | Binary Search template from memory | DSA | MUST | 25 | Not Started | Day10_Sorting_BinarySearch
14 | Fri 14 Aug | Afternoon | Max Depth of Binary Tree | DSA | MUST | 25 | Not Started | Day11_Trees
15 | Fri 14 Aug | Afternoon | Timed drill: 2 Easy problems in 40 minutes | Mock | MUST | 40 | Not Started | Timer on phone
16 | Fri 14 Aug | Afternoon | Rewrite all FAIL problems once | DSA | MUST | 40 | Not Started | List fails in My Notes
17 | Fri 14 Aug | Evening | Speak Intro Version A (under 2 minutes) | Resume | MUST | 15 | Not Started | INTRO.md
18 | Fri 14 Aug | Evening | GeoVerse 1-min pitch + 1 difficulty | Resume | SHOULD | 15 | Not Started | PROJECT_DEPTH.md
19 | Fri 14 Aug | Evening | AWS pipeline 1-min pitch + 1 difficulty | Resume | SHOULD | 15 | Not Started | PROJECT_DEPTH.md
20 | Fri 14 Aug | Evening | HR: Strength + Weakness + Why hire you | HR | MUST | 20 | Not Started | BEHAVIOURAL.md / PDF
21 | Fri 14 Aug | Evening | CS: ACID properties with UPI example | CS | MUST | 15 | Not Started | DBMS_SQL/03
22 | Fri 14 Aug | Evening | CS: Deadlock 4 conditions + real example | CS | MUST | 15 | Not Started | OS/02
23 | Fri 14 Aug | Evening | CS: TCP vs UDP + HTTP vs HTTPS + DNS | CS | MUST | 20 | Not Started | CN notes
24 | Fri 14 Aug | Evening | OOP 4 pillars with tiny Python example | CS | SHOULD | 15 | Not Started | CS_Core/OOP.md
25 | Sat 15 Aug | Morning | Re-solve ONLY failed DSA problems | DSA | MUST | 90 | Not Started | No new topics
26 | Sat 15 Aug | Afternoon | FULL MOCK: Intro → 2 DSA → Nyay → CS → HR | Mock | MUST | 75 | Not Started | Day14_FULL_MOCK_SCRIPT.md
27 | Sat 15 Aug | Afternoon | Write top 5 weak answers and fix same day | Mock | MUST | 45 | Not Started | Notebook / Notes col
28 | Sat 15 Aug | Evening | Flash revise CHEATSHEET + CS QUICK_REVISE | Revise | MUST | 30 | Not Started | CHEATSHEET.md
29 | Sat 15 Aug | Evening | Final speak: Intro + Nyay + Why hire you | Resume | MUST | 20 | Not Started
30 | Sat 15 Aug | Night | Sleep before 11 PM. No new coding. | Health | MUST | 0 | Not Started | Critical for performance
31 | Sun 16 Aug | Morning | 15 min only: Intro + Nyay Sahayak | Interview | MUST | 15 | Not Started | No new DSA
32 | Sun 16 Aug | Morning | Water + resume ready + calm breathing | Interview | MUST | 10 | Not Started
33 | Sun 16 Aug | Interview | Use formula: Clarify→Example→Brute→Better→Code→Complexity | Interview | MUST | 0 | Not Started | Keep in mind
QUICK COUNTS
Done: |  | In Progress: |  | Not Started:
MUST completed: |  | MUST total: |  | % MUST done:

## 02_DSA_Problems
02 — DSA MUST PROBLEMS (Brute + Optimal)
Interview habit: explain brute first, then code optimal, then say Time & Space.
# | Problem | Pattern | Brute Idea | Optimal Idea | Coded? | Explain T/S? | Status | Confidence (1-5)
1 | Two Sum | Hash Map | Check all pairs O(n²) | Hash map value→index O(n) | No | No | Not Started
2 | Contains Duplicate | Hash Set | Nested loops | Use set / compare lengths | No | No | Not Started
3 | Best Time to Buy/Sell Stock | One Pass | Try all buy/sell pairs | Track min price so far | No | No | Not Started
4 | Move Zeroes | Two Pointers | Build new array | Write pointer in-place | No | No | Not Started
5 | Valid Parentheses | Stack | Count only (incomplete) | Stack + matching pairs | No | No | Not Started
6 | Valid Palindrome | Two Pointers | Clean string + reverse | L/R pointers skip junk | No | No | Not Started
7 | Longest Substring No Repeat | Sliding Window | Generate all substrings | Window + last-seen map | No | No | Not Started
8 | Reverse Linked List | Pointers | Copy values to array | prev / curr / next reverse | No | No | Not Started
9 | Binary Search | Divide & Conquer | Linear scan O(n) | Mid cut half O(log n) | No | No | Not Started
10 | Max Depth of Binary Tree | DFS / Recursion | BFS level count also ok | 1 + max(left, right) | No | No | Not Started
11 | Majority Element (bonus) | Hashing | Count with dict | Counter / Boyer-Moore optional | No | No | Not Started
12 | First Unique Character (bonus) | Hashing | Nested scan | Counter then one pass | No | No | Not Started
SPEAK TEMPLATE IN INTERVIEW
1) Clarify input/output 2) Dry-run example 3) Brute force + complexity 4) Optimal + complexity 5) Code 6) Edge cases
Done count: |  | Avg confidence:

## 03_Resume_HR
03 — RESUME + HR SPEAKING TRACKER
Mark Done only when you can speak without reading notes.
# | Item | Must Cover | Target Time | Without Notes? | Status | Last Practiced
1 | Intro Version B (short) | Name, college, CGPA, AWS cert, 3 projects short, role goal | 60–75 sec | No | Not Started
2 | Intro Version A (full) | Short family + projects + hackathons + photography + close | 90–110 sec | No | Not Started
3 | Nyay Sahayak deep dive | RAG flow, ChromaDB+Groq, roles, IPC↔BNS, difficulty, next improvement | 3 min | No | Not Started
4 | What is RAG? | Retrieve relevant docs, then generate; reduces hallucination | 45 sec | No | Not Started
5 | GeoVerse pitch | Live APIs, AI itinerary, fallback, lazy routes/cache | 60 sec | No | Not Started
6 | AWS Intelligence Loop | Lambda + Comprehend + DynamoDB + QuickSight + one difficulty | 60 sec | No | Not Started
7 | Strength | Ship usable products (auth/fallback/RAG) + hackathon calm | 45 sec | No | Not Started
8 | Weakness | Earlier surface-level; mock said needs depth; now practice depth daily | 45 sec | No | Not Started
9 | Why hire you? | Learn fast + shipped projects + AWS cert + ownership mindset | 45 sec | No | Not Started
10 | STAR hardest bug | Nyay ungrounded answers → improved retrieval/RAG → learning | 60–90 sec | No | Not Started
11 | 3–5 year vision | Own features end-to-end; later mentor juniors; now fundamentals | 40 sec | No | Not Started

## 04_CS_Core
04 — CS CORE FLASH CARDS
Answer style: Definition + small example + why it matters in real systems.
# | Subject | Question | Answer Keywords | Can Speak? | Status | Revise Count
1 | DBMS | Primary key vs Foreign key | PK uniquely identifies row; FK links to another table | No | Not Started | 0
2 | DBMS | INNER JOIN vs LEFT JOIN | INNER=matches only; LEFT=all left rows + matches | No | Not Started | 0
3 | DBMS | ACID (with UPI example) | Atomicity Consistency Isolation Durability | No | Not Started | 0
4 | DBMS | What is an Index? | Faster reads; slightly slower writes | No | Not Started | 0
5 | DBMS | Normalization meaning | Reduce duplication and update anomalies | No | Not Started | 0
6 | OS | Process vs Thread | Process=own memory; Thread=shared memory workers | No | Not Started | 0
7 | OS | Deadlock 4 conditions | Mutual exclusion, Hold&Wait, No preemption, Circular wait | No | Not Started | 0
8 | OS | Virtual memory / page fault | Use disk as extra memory; fault loads missing page | No | Not Started | 0
9 | CN | TCP vs UDP | TCP reliable ordered; UDP faster, less reliable | No | Not Started | 0
10 | CN | HTTP vs HTTPS | HTTPS = HTTP + TLS encryption | No | Not Started | 0
11 | CN | DNS purpose | Converts domain name to IP address | No | Not Started | 0
12 | OOP | Four pillars + example | Encapsulation, Abstraction, Inheritance, Polymorphism | No | Not Started | 0
13 | SE | Agile vs Waterfall | Agile=sprints+feedback; Waterfall=sequential stages | No | Not Started | 0
14 | SQL | Write JOIN + GROUP BY query | Practice from CS_Core/DBMS_SQL/04_sql_practice.md | No | Not Started | 0

## 05_Interview_Day
05 — 16 AUG INTERVIEW DAY
Keep this sheet simple. No new learning. Execute calmly.
# | Checklist Item | Status | Notes
1 | Slept well the night before | Not Started
2 | Light breakfast + water bottle ready | Not Started
3 | Resume PDF / print ready | Not Started
4 | Laptop + internet checked (if online interview) | Not Started
5 | 15 min revise ONLY: Intro + Nyay Sahayak | Not Started | No new coding
6 | Reach venue / join link 10 minutes early | Not Started
7 | Greet interviewer calmly; smile once | Not Started
8 | DSA formula ready in mind: Clarify→Example→Brute→Better→Code→T/S | Not Started
9 | If stuck: explain brute force first, then optimize | Not Started
10 | Be honest about any resume number you cannot defend | Not Started
11 | Ask 1 good question at end (team stack / mentorship) | Not Started
12 | After interview: write questions asked + mistakes | Not Started | Learn for next round
FINAL LINE TO REMEMBER
You already built real projects. In this interview, show clear thinking. One round does not define your whole career.

## 06_Weak_Log
06 — WEAK LOG (write fails here)
Every fail becomes a revision item. Fix within 24 hours.
# | Date | Topic / Problem | What went wrong | Fix / Correct idea | Fixed?
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15